## Sheet1
2021-10-15
BAD FORECAST…CHECK TEXT BLAST BEFORE YOU LEAVE IN THE MORNING !!!!
Time | Employee | Job | Job # | Contact | Truck # | Load List
ON SITE | 140 DON ENGEL* | HOFFMAN i94-BL : EAST AVE-PAGE AVE | 211295 | ERIC 517-795-3722 | 467 | REG LOAD
7:30 | 69 DERRICK KALOCY* | WB: 12H-4Y | JACKSON | INSP REED 517-262-8879 | 511 | STRIPER
7:30 | 28 DYLAN BOLDT* | CHECK IN ON WEST SIDE 94 JOBS |  |  | 416 | REG LOAD
7:30 | 1076 CARSON CRABTREE
7:30 | 148 DAN DEVINE* | CADILLAC CANTON 2021 MAJOR ROADS | 211192 |  | 469 | REG LOAD
8:00 | 42 ALFONSO MEDINA* | PHASE 1 WB 2ND APP : 24H-4W, 26T-4Y, 56H-6W | WAYNE | FTCH ALI 248-410-7411 | 512 | STRIPER
8:00 | 363 DANIEL SIMON* | SHELDON RD @ FORD + 1 OTHER LOCATION |  |  | 425 | LARGE 270 - 10 RLS 6" 271
8:00 | 1154 JONATHAN PRCHLIK | NEED YELLOW XH
OXFORD 7:30 AM | 147 TYLER MOST* | MDOT 2021 BAY | 213012 |  | 468 | REG LOAD
OXFORD 8:00 AM | 1068 JULIO SUSTAITA* | CALL BACK | ST CLAIR | BRENT-989-751-3873 | 513 | STRIPER
OXFORD 8:00 AM | 1143 MATT WEST*
OXFORD 8:00 AM | 1025 TYLER PROSSER* |  |  |  | 721 | 1 TOTE W&Y, 2 BEADS, 300 CONES
OXFORD 8:00 AM | 1188 BRODY KINNUNEN
AFT APT | 74 NATE BLUMERICH* | MISC DETROIT RECON |  |  | 474 | REG LOAD
OXFORD 7:30 AM | 320 MIKE MYER* | RIETH-LAN M-52/ WERKNER RD | 211229 | SHAWNDELL 517-599-2849 | 466 | REG LOAD
OXFORD 8:00 AM | 126 KEVIN CLARK* | NR WR 6W, 10T | WASHTENAW | PAT MCMURPHY 586-924-2156 | 505 | STRIPER - PICK UP IN TROY ON WAY TO JOB
OXFORD 8:00 AM | 1209 JACOB DECLAIRE*
6:00 | 60 ERNESTO MEDINA* | DAN'S i69: FENTON-DORT HWY (M54) BRIDGES | 217036- | DOUG STROMAN 810-217-3015 | 1006 | WATERBLASTER
|  | WATERBLASTING PREP | GENESEE | BURT 810-533-5237
INSP MIKE ROYALTY 810-859-5120
7:00 | 106 ANDY TUCKER* | FT WAYNE PW7023 CONNER IMPROVEMENTS | 201419 | MIKE P 248-388-5623 | 445 | REG LOAD
9:00 | 1072 JASON JURGENS* | LARGE RECONFIG: WARREN TO JEFFERSON READY | WAYNE | INSP STEVE 734-790-5596 | 521 | YARD FIRE 6:00 AM
7:00 | 123 ALEX GARZA | CADILLAC M153/MERCURY-WYOMING HMA REPAIR | 211294 | STEVE 734-740-4423
9:00 | 1051 KYLE PREW* | FINAL STP: 11T-4W | WAYNE | INSP LUIS 313-949-3752 | 238 | LOAD PER AIKIN
9:00 | 1149 CURTIS CANNON* | CADILLAC INDEPENDENCE TWP 2021 | 217006 | CHERILYN 734-447-0219 | TROY 6 POT | YARD FIRE 6:00 AM
|  | STP: CLARKSTON RD | OAKLAND | INSP ANDREAU 248-466-4529
7:00 | 132 DAVE AIKIN* | CADILLAC M153/MERCURY-WYOMING HMA REPAIR | 211294 | STEVE 734-740-4423 | 439 | REG LOAD & 2 BUCKETS OF SHOT
7:00 | 1071 PATRICK BECKETT | LAYOUT FOR FINAL STP: 11T-4W | WAYNE | TYME DARRYL 734-502-8201
7:00 | 76 JASON ZMIJA* | FT WAYNE PW7023 CONNER IMPROVEMENTS | 201419 | MIKE P 248-388-5623 | 436 | REG LOAD
7:00 | 167 SAMANTHA SCHONFELD* | LAYOUT & GREEN EB IF WEATHER ALLOWS | WAYNE | INSP STEVE 734-790-5596 | 514 | LOAD PER Z
7:00 | 391 ALLEN WILMAN |  |  |  | 447 | LOAD PER Z
8:00 | 1198 NOAH HADEN |  |  |  | 443 | LOAD PER Z
8:00 | 1210 ANDREW LEICHTY
8:00 | 1204 MICHAEL EMRICK
OXFORD 6:30 AM | 1034 KURTIS KING* | HOFFMAN i94-BL : EAST AVE-PAGE AVE | 211295 | ERIC 517-795-3722 | 596 | DETAIL POLY
OXFORD 7:00 AM | 1186 SAUL MALDONADO | POLY 2H-6CW, YIELD TRIANGLES -16 EA | JACKSON |  | 426 | POLY SUPPORT
OXFORD 7:00 AM | 1137 ALEX VANLUVAN
9:00 | 1065 BRYAN VANLUVEN* | FONSON 11 MILE RD: MIDDLEBELT-INKSTER | 211071 | JEHNNA 810-222-9815 | 419 | LARGE 270 - 15 BIKE DUDES
9:30 | 1196 NICK SANDLER | CP: 13 BIKE W/ ARROW, 8H-6CW, 3H-24SB, 6-LTA, 5-RTA, 5 SHARROWS | OAKLAND | INSP ALLYSSA 734-486-5822 | 422 | LARGE 270
9:30 | NICHOLAS BURGESS
CALL AFT APT | 130 RAY HERRIN* | CALL AFT APT
OUT | 84 HUNTER LUIKART* | MPM-GR I196/130th AVE-M40 | 212063- | Chad (MPM) (616) 307-4304 | 814 | REG LOAD
OUT | 365 COREY KIRBY* | RE-RECESS POLY DD 4 MILES | ALLEGAN | George Heath (231) 750-4411 | 530 | STRIPER
OUT | 1160 SAM HADEN | NAGEL OTTAWA AVE/FULTON ST-MICHIGAN ST | 212108- | BRUCE 616-293-0962 | 716 | LOAD PER C KIRBY
|  | POLY WR ON TOP LL. 4"W 5,565/4"Y 840' | KENT
OUT | 99 TOMAS JASSO* | MPM-GR I196/130th AVE-M40 | 212063- | Chad (MPM) (616) 307-4304 | 921 | LEFT 7" FLATS, RIGHT 7" MILLING HEAD
OUT | 1005 CODY CRABTREE* | RECESSING FOR POLY | ALLEGAN | George Heath (231) 750-4411 | 916 | LEFT 7" MILLING HEAD, RIGHT 7" FLATS, 5" FLATS ON BACK
OUT | 1058 RONALD WILLIAMS* |  |  |  | 435 | BLOWER
OUT | 1187 ROGELIO DELGADO-JIMENEZ* |  |  |  | 227 | BLOWER
OUT | 118 BRENT STAFFORD* | BOLEN COUNTY RD 491 / ANDERGOOD RD - CR 612 | 214155- | MATT (BOLEN) 989-305-0224 | 905 | GROOVER 5" & 7" BOTH SIDES
OUT | 1115 YONATHAN ROSILLO* | RECESSED POLY DD (4Y=19000', 6W=47000') | MONTMORENCY | GLEN (INSP) 989-657-3121 | 904 | GROOVER 5" & 7" BOTH SIDES
OUT | 1078 CHARLES WOOTEN* | BOLEN COUNTY RD 487 / M32 - CR 489 | 214154- | MATT (BOLEN) 989-305-0224 | 242 | ATTENUATOR BLOWER
OUT | 1203 JOSEPH DAWSON | RECESSED POLY DD (4Y=6600', 6W=9600') | MONTMORENCY | GLEN (INSP) 989-657-3121 | 710 | ATTENUATOR BLOWER
OUT | 1043 JASON ALBENSI* | BOLEN COUNTY RD 491 / ANDERGOOD RD - CR 612 | 214155- | MATT (BOLEN) 989-305-0224 | 531 | STRIPER
OUT | 71 KYLE KIRBY* | RECESSED POLY DD (4Y=19000', 6W=47000') | MONTMORENCY | GLEN (INSP) 989-657-3121 | 813 | REG LOAD
OUT | 138 CHAD RYERS* | BOLEN COUNTY RD 487 / M32 - CR 489 | 214154- | MATT (BOLEN) 989-305-0224 | 424 | BLOWER 2 PALLETS BEADS
OUT | 1164 JR CASTILLO | RECESSED POLY DD (4Y=6600', 6W=9600') | MONTMORENCY | GLEN (INSP) 989-657-3121 | 243 | ATTENUATOR W/ TOTE W & Y, 4 CAT, 4 POLY U BLEND
OUT | 1169 DWANE STIGER*
OXFORD 6:00 AM | 1045 DAVID MILLER* | RIETH-HD M27/I75NB EXIT RAMP - WOODSIDE PARK RD | 214082- | TAYLOR (RIETH) 989-370-0582 | 971 | RUMBLE TRUCK
OXFORD 6:30 AM | 1022 RYAN MAAS | CENTER CORRUGATIONS (NEW HMA) = 58266' LFT (13 MILE JOB) | CHEBOYGAN | NICK (OHM) 517-930-1645 | 805 | PER DAVE / AS LOADED
OXFORD 6:30 AM | 1142 JUSTIN BROWN* | BRING GEAR |  |  | 798 | VACALL
OXFORD 6:30 AM | 1133 JACK WILLIAMS* |  |  |  | 103 | DUMP WITH CONVAYOR BROOM
OXFORD 6:30 AM | 1063 JOSH STROMME*
OXFORD 6:30 AM | 1190 PATRICK OGG |  |  |  | 432 | SIGNS, WALKIE TALKIES
OXFORD 6:30 AM | 1102 CHRISTIAN SMITH |  |  |  | 836 | PILOT CAR SIGNS
OXFORD 6:30 AM | 1118 ABBEY BURCH |  |  |  | 232 | STOP SLOW PADDLES, HARD HATS
OXFORD 6:30 AM | 1208 KENITH POST |  |  |  | 427 | BLOWER
OUT | 165 VICTOR GARZA* | ANN ARBOR 2021-2022 MARKINGS | 211205 |  | 449 | REG LOAD, THERMO CARTS
OUT | 149 GENARO GARZA | HP HW PER ADAM | WASHTENAW | ADAM AJAM 734-323-5656
OUT | 1159 OSCAR CASTILLO* | CADILLAC 2020 ANN ARBOR | 201245 |  | 620 | FIRE PER VICTOR
|  | HP HW PER GARY | WASHTENAW | INSP GARY 734-765-8154
|  | BAILY EXC DUNMORE WAVERLY, WELDON, HARTFORD | 211266 | JACOB 517-740-0371
|  | HP: 1H-24 SB | WASHTENAW | INSP KEVIN 248-990-0794
ADDING OUTLINE OF CW
7:00 | 1056 SAMANTHA KISCHUK | MAJOR PW 7019 RESIDENTIAL STREETS | 211319 | JOE 248-285-2429 | 598 | DETAIL POLY
7:30 | 1120 DASHAWN MAYS | POLY HW IN GROOVE | WAYNE | DETROIT INSP TBD | 459 | POLY SUPPORT
7:30 | 1162 RENATO VILLARREAL | SEE NATE- START @ LOC #4 CIRCUIT FOR TEAMS
7:30 | 1213 RAVEN CHALTRAW
6:00 | 1013 DENNY MATHEWS* | MAJOR PW 7019 RESIDENTIAL STREETS | 211319 | JOE 248-285-2429 | 448 | SCB 7" FLATS
6:30 | 1128 JORDAN LUPRO | RECESSING FOR POLY HW | WAYNE | DETROIT INSP TBD | 821 | SCB 13" FLATS
6:30 | 117 MIKE PHELAN* |  |  |  | 824 | SWEEPER
8:30 | 124 RICK VELLUCCI* | WARREN 2021 MARKINGS | 211287 | INSP CHRIS 586-291-3867 | 820 | LARGE 270
9:00 | 1038 LUZ HERNANDEZ* | CP: 23T-6"CW, 2T-24SB, 3T-18"SB | MACOMB | INSP ROB 586-291-6038 | 421 | LARGE 270
7:00 | 1127 DAVID CAMPBELL | MAJOR PW7035 DETROIT 2021 SPEED HUMPS VAR LOC | 211206- | DAN 248-207-7819 | 228 | DETAIL POLY
7:30 | 1101 JORGE LUNA | POLY SPEED HUMP SYMBOLS LIST #11 | WAYNE | INSP RAUL 313-220-8783 | 434 | POLY SUPPORT
7:30 | 1156 MARIO PEREZ
9:00 | 1060 DREW HUFFMAN | AJAX 12 MILE RD: FARMINGTION RD- ORCHARD LAKE | 211237 | BRIAN 248-561-2461 | 420 | LARGE 270 - BLIP BASKET, LEGEND GRINDER
|  | CPI INLAY: 3H-18SB, 13H-6CW, 3 EA-T&LTA RAB | OAKLAND | RCOC STEVE 248-752-7087
7-LTA, 7-RTA, 2-SCH
4:00 | 328 SCOTT LUIKART* | TROY SHOP
5:00 | 3001 LUIS MORRIS
NOON | 371 JEREMY ROOSEN*
18:00 | 142 YERIK GARZA*
OXFORD 5:00 AM | 1044 ROGER HENDERSON* | OXFORD SHOP
OXFORD 10:00 AM | 381 DAVE CONRAD*
OXFORD NOON | 1183 HAYDEN BORISENKO
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD
REBUILD